## Project Planner
Project Gantt Chart
[5 empty] | Period Highlight: | 25 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | WEEKS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Literature review, finalizing project requirements | 1 | 4 | 1 | 4 | 100%
Lab setup (Ubuntu forensic server, Windows VM, Sysmon, dependencies) | 1 | 3 | 1 | 2 | 100%
Develop memory forensics and ransomware detection modules (Volatility + YARA integration) | 3 | 4 | 3 | 7 | 100%
Implement log parser and correlation engine | 4 | 10 | 6 | 9 | 100%
Develop cloud forensic collectors and integrate dashboard/report generator | 6 | 10 | 6 | 14 | 100%
System integration and refinement; debugging | 14 | 3 | 15 | 6 | 100%
Testing and evaluation using synthetic ransomware scenarios | 16 | 2 | 16 | 5 | 100%
Documentation, report writing, and final presentation | 16 | 4 | 19 | 7 | 100%